{"text_format":"2","workbook":"xlsx","n_sheets":2,"sheets":["STD开发任务清单","Sheet2"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"STD开发任务清单","index":0,"n_rows":15,"n_cols":11,"rows_kept":15,"cut":false,"hidden":false,"merged":[[0,0,0,10]]}
["BBA发运系统程序开发与单元测试"]
["开发任务",null,null,"开始日期","结束日期","演示日期","状态","百分比","描述","开发人员","备注"]
["LAB导入STD系统 增加版本验证，保留历史版本，增加对比、在途验证与调整",5,null,"2022-02-08","2022-02-14","2022-03-21","Open",0,"LAB导入STD，增加版本验证，保留历史版本，增加对比、在途验证与调整","刘洪辉","核心功能"]
["材料翻箱成品追溯记录——STD",3,null,"2022-03-23","2022-03-24","2022-03-30","Open",0,"扫描材料标签，扫描成品标签，记录追溯关系——防错不考虑","金浩、崔亮","非紧急核心功能"]
["BBA VDA标签生成文件——STD",2,null,"2022-02-20","2022-02-21","2022-03-21","Open",0,"按照客户VDA标签格式打印","刘洪辉","核心功能"]
["BBA ASN打印生成文件——STD",2,null,"2022-02-22","2022-02-23","2022-03-21","Open",0,"按照客户ASN单据格式打印","刘洪辉","核心功能"]
["BBA Pre-DN生成文件——STD",2,null,"2022-02-24","2022-02-25","2022-03-21","Open",0,"按照客户Pre-DN文件生成CSV或者excel文件，SFTP上传到指定服务器目录","刘洪辉","核心功能"]
["客户需求发货跟踪报告——STD",5,null,"2022-02-26","2022-03-04","2022-03-30","Open",0,"根据每个零件最新的releaseID创建最新版本的发货计划，锁定需求执行发货，实时对比最新LAB与发货计划的差异，由用户决定是否重新更新发货计划；\n计划数量-LAB 客户库位、备货数量-PickList、发货数量-ASN跟踪对比，LAB更新调整警告（）","刘洪辉","非紧急核心功能"]
["发货校验照核扫描——STD",2,null,"2022-03-05","2022-03-06","2022-03-21","Open",0,"VDA左右标签&内部箱标签扫码照核，与ASN比对，确保标签一致，与发货计划一致","刘洪辉","核心功能"]
["ASN发货前调整——STD",2,null,"2022-03-09","2022-03-10","2022-03-21","Open",0,"发运前宝马临时变动，导致的ASN内部的调整，增、删、改，以及koli号的调整，更换标签工作","刘洪辉","核心功能"]
["ASN确认发送——STD",2,null,"2022-03-11","2022-03-12","2022-03-21","Open",0,"装车校验完成后，确认ASN发送通知，发送前确认LAB无更新，若有更新，则提醒，如果有差异做成用户可以选择继续、还是暂停","刘洪辉","核心功能"]
["ASN取消——STD",2,null,"2022-03-13","2022-03-14","2022-03-21","Open",0,"ASN发送以后由于特殊情况取消ASN，退回重新启用新的ASN进行处理","刘洪辉","非紧急核心功能"]
["VDA标签作废——VDA查看内部标签号，内部标签重新校验贴标签；",2,null,"2022-03-25","2022-03-26","2022-03-30","Open",0,"STD提供枪端程序允许扫描VDA标签查看对应原内部标签参考号，在QAD系统通过内部标签参考号补打标签，STD提供枪端程序扫描内部标签、VDA标签做照核，只有匹配关系一致才允许通过，实物贴内部标签即可，STD系统将原匹配关系作废；","金浩、崔亮","非紧急核心功能"]
["下架任务文件生成",4,null,"2022-02-18","2022-02-19","2022-03-21","Open",0,"STD系统中在PRE-DN创建完成后，允许用户点击生成下架任务接口文件，汇总零件数量，该文件导入QAD创建7.9.2预先发货单，驱动AIM创建下架任务；","金浩、崔亮","核心功能"]
["SUPPLIERNET发货如何补录关联",7,null,"2022-03-21","2022-03-30","2022-04-15","Open",0,"1，SpplierNet平台下载LAB，导入STD系统；——提供CSV文件，分析判断；\n2，STD正常创建PRE-DN，ASN，VDA标签，校验发货；\n3，SupplierNET上创建与STD系统ASN号码一致的BBA ASN，打印VDA标签与ASN；\n4，STD提供BBA VDA标签与STD VDA标签照核，创建匹配关系，防错——STD ASN更新状态，防止重新发送ASN；\n5，SupplierNET上做ASN发送确认；","刘洪辉","非紧急核心功能"]

{"sheet":"Sheet2","index":1,"n_rows":12,"n_cols":16,"rows_kept":12,"cut":false,"hidden":false,"merged":[]}
[null,"day1","day2","day3","day4","day5","day6"]
["需求 LAB",100,80,130,90,110]
["累计收货LAB",0,100,100,230,330]
["在途",0,0,80,0,0,null,null,"系统","客户需求",null,"先前累计需求——过去时间累计数量"]
["累计发运 STD",0,100,180,230,330]
["应发 STD生成发货计划",{"$f":"B2-B4","v":100},80,{"$f":"D2-D4","v":50},90,110,{"$nulls":4},"先前累计需求",{"$nulls":4},"累计发运"]
["实际发运",100,80,50,100,{"$nulls":4},"版本1",0,"day1","day2","day3","day4",0]
[{"$nulls":11},100,100,100,100]
[{"$nulls":10},100,"day2","day3","day4","day5",120]
[{"$nulls":9},"版本2",null,100,100,100,100,60]
[{"$nulls":10},"净需求",80,100,100]
[{"$nulls":11},140,"MRP、发运"]